## Consolidated
Consolidated | Estimated Time
UX Design and Prototyping | ~ 5-8 hours
Set up skeleton | 1 hour
Set up firebase config and db | 30 min
Set up firebase auth | 1 hour
Obtain Spority API credentials running | 30 min
Call spotify API's "Get User's Top Artists and Tracks" | 1 hour
Create user's database table with top artists and tracks | 30 min
Make the frontend connect with backend that stores the obtained top artists data into database | 2 hours
Create a modal when user sign up/ log in asking them to enter their instruments and store in database | 1 hour
Write queries to manage user profiles | 1 hour
Create a page to display user's top artists that was obtained and stored. | 2 hours
Write queries to search through other user's top artists data | 1 hours
Write functions to match with other user's top artists and calculate a similarity score | 2 hours
On the same page, display similar users with similar tastes of music (aka similar top artists) | 1 hour
Implement function that allow users to send invitations to other users that are on the list | 1 hour
create top header with filters of instruments users play and display filtered data | 1 hour
For each matched results, display each one of them in a box | 30 min
Add responsive button to request connections with the matched users | 1 hour
Create a user profile page that displays their basic info, and top artists | 1 hour
On the user profile page, add the display of the connected users | 1 hour
On the user profile page, add display of the requests received from other users | 1 hour
For each received requests, create responsive buttons to accept or dismiss the invites | 1 hour
Once the user accepts or dismisses the invites, update the database on firebase | 2 hours
Display the accepted friend invites between users on their profile page | 1 hour

## individual estimation
Yunhan Huang | Estimated Time | Zhaoguo Zhu | Estimated Time | Yingyun Zhan | Estimated Time | Yinghao Zheng | Estimated Time
Set up firebase database | 20 min | User Story Visual Design | 24 hour | Login page design | 2 hours | The basic chatting frame from third party. | 4 hours
Set up firebase auth | 30 min | Building Skeleton Code for the Website | 24 hour | Set up Spotify account authorization | 1 hour | The building of group chatting frame. | 4 hours
Create user's database table with top artists and tracks | 1 hour | Set up Spotify API to require users' data | 30 min | Design a list box for users to choose their instruments | 1 hour | Create database for top artists and bands. | 3 hours
Set up spotify API credentials | 1 hour | Set up Spotify crendentials to require users to enter their Spotify accounts information | 30 min | Create a database table to store users' instrument preferences | 1 hour | Visual design of UI page. | 4 hours
Call spotify API's "Get User's Top Artists and Tracks" | 1 hour | Call spotify API's "Get User's Top Artists and Tracks" | 30 min | Write an algorithm to filter out users with similar instruments | 3 hours | Design an algorithm to compare certain user's top 10 with all users' in the database. | 4 hours
Make the frontend connect with backend that stores the obtained top artists data into database | 1 hour | List all Users in Descending orders of mutual favorite Artists and Tracks compared with the main Users. | 1 hour | Create a database table to store users' top 10 artists | 1 hour | Give a score to all the users who have at least one mutual taste on the artists with current user. | 6 hours
Create a modal when user sign up/ log in asking them to enter their instruments and store in database | frontend ~1 hour, backend 20 min | Creating a pop out windows to ask Users to enter their personal information | 30 min | Write an algorithm to match the user with other users according to their preferences | 3 hours | Display the users who have a score in descending order on a page. | 2 hours
Write queries to manage user profiles | ~1 hour | Store users' data into database | 1 hour | Web page design for displaying matched users results | 2 hours | Create a page that user can edit his/her preference. | 3 hours
Create a page to display user's top artists that was obtained and stored. | Frontend 2 hours, backend 3 hours | Display Users' data while presenting the "musician with mutual favorite artists" list | 1 hour | Establish the fuction of friend invitation | 2 hours | Add an "adding" link below every scored user to build connection. | 2 hours
Write queries to search through other user's top artists data | 1 hour | Implement function that allow users to send invitations to other users that are on the list | 1 hour | Create a database table to store the relationships of users | 1 hour | Add an "accept" link below every user who has sent friend request. | 2 hours
Write functions to match with other user's top artists and calculate a similarity score | 2 hours | Display a pop out windows to confirm users request for sending invitation | 30 min | Once the relationship is built between two users, create a new database to store their messages communicated | 1 hour | Set up Spotify API to require users' data | 2 hours
On the same page, display similar users with similar tastes of music (aka similar top artists) | Frontend 2 hours, backend 2 hours | Display a pop out windows to the receiving ends that display the invitation | 30 min | User profile page design: connected users, preferences, posts, requests received but not yet responded | 5 hours | Create database for instrument. | 3 hours
create top header with filters of instruments users play and display filtered data | Frontend 1 hour | Create response key to whether accept the invitation or not | 1 hour | Design a funcation of notifications to notify there is requests received or new friend accept your invitation | 2 hours | Give a score to all the users who have the same instrument preference based on distance. | 6 hours
For each matched results, display them in a box | Frontend 3 hours, backend 1 hour | Create a list that display all the users that have connection with the host user | 1 hour |  |  | Display the users who have a score in descending order on a page. | 2 hours
Add responsive button to request connections with the matched users | Frontend 30 min, backend 1 hour | Set up Google Map API for Secondary User story of under this Primary User Story branch | 1 hour |  |  | Using GMap API to get the location info of user. | 3 hours
Create a user profile page | Frontend 1 hour | Set up Google account credentials to require users to enther their google acconts information | 30 min
On the user profile page, display connected users | Frontend 1 hour, backend 1 hour | Call GMap API to require information of users' locations | 30 min
On the user profile page, display the requests received from other users | Frontend 1 hour, backend 1 hour | Store users' information of locations as a mutable varaible in the database | 1 hour
For each received requests, create responsive buttons to accept or dismiss the invites | Frontend 30 min, backend 1 hour | Display on the map view of nearby musicians in 5 miles with their short personal information | 1 hour